AIA MONTHLY BILLING

Monthly Deadline Cheat Sheet & Checklist

Billing rule: Only completed work is invoiced. Incomplete work moves to next month's invoice.

| DONE | DATE | OWNER | REQUIRED ACTION | PROOF / OUTPUT |
| --- | --- | --- | --- | --- |
| ☐ | 1st-19th | PM/APM + Superintendent | Track completed work; keep Daily Logs, documentation, and Three-Week Lookahead current. | Current records |
| ☐ | 19th | PM/APM + Superintendent | Complete joint billing review; agree on complete work and supportable percentages. | Agreed percentages + exception list |
| ☐ | 20th | PM/APM | Receive/review subcontractor invoices and CPRs; complete Pen Req; send to Mike for QC. | QC submission |
| ☐ | 21st | Superintendent | After Mike's approval, contact COR and schedule the billing walkthrough with PM awareness. | Walkthrough scheduled |
| ☐ | By 23rd | PM + Superintendent + COR | Complete Government/COR walkthrough and review completed work and billing percentages. | COR feedback documented |
| ☐ | Same day | Superintendent -> PM | Send approvals, questions, percentage changes, and any items to remove or revise. | Complete feedback sent |
| ☐ | 24th | PM/APM + Superintendent | Complete revisions, resolve all COR comments, and confirm final CO/COR buy-in. | Final buy-in |
| ☐ | 25th-27th | PM/APM + Cashmere/Sue | 25th approved Pen Req to Cashmere/Sue; 26th notarization/Drew signature; 27th AIA to CO/COR. | Final AIA out for signature |
| ☐ | 29th | PM/APM | Return CO/COR-signed AIA to Cashmere. | Signed AIA received |
| ☐ | Last business day + 48h | Cashmere/Sue | Upload to Tungsten; within 48 hours verify movement and follow up if still in Received status. | Upload + status confirmation |

ROLE FINISH LINES

| PM/APM: Control the package through CO/COR signature and return the signed AIA to Cashmere by the 29th. | SUPERINTENDENT: Verify field completion, secure COR buy-in, and deliver all feedback to PM by the 24th. |
| --- | --- |

DOMINO WARNING: Missing records -> late Pen Req/QC -> late walkthrough/buy-in -> compressed signatures -> delayed upload and payment processing. Escalate early with the risk, impact, owner, due time, and recovery plan.