AIA Monthly Billing Process-PM/APM

Step-by-Step Guide

Billing Rule: Only work completed by the billing cutoff is invoiced. If it is not complete, it moves to the next month's invoice.

1. Track Project Progress

Due: Ongoing – 1st through 19th

- PM and Superintendent track completed work.

- Keep Daily Logs, project documentation, and Three-Week Lookaheads current.

2. Collect & Review Subcontractor Invoices

Due: No Later Than the 20th

- Review subcontractor invoices as they come in.

- Confirm invoices match work completed onsite.

- All subcontractor invoices must be received by the 20th.

3. Collect CPRs

Due: With Subcontractor Invoices / No Later Than the 20th

- Collect required Certified Payroll Reports (CPRs) as invoices come in.

- Follow up immediately on missing CPRs.

4. Review Completed Work with Superintendent

Due: 19th

- PM and Superintendent review what is actually complete.

- Confirm subcontractor billing matches field progress.

- Identify anything that should not be billed.

5. Prepare the Pencil Requisition

Due: 20th

- Include completed work only.

- Work not complete by the billing cutoff moves to the next invoice.

- Confirm billing percentages are accurate.

6. Complete Superintendent Review

Due: 20th

- PM and Superintendent complete a final review of the Pen Req.

- Make corrections before submitting for QC.

7. Send Pen Req to Mike for QC

Due: 20th

- PM sends the completed Pen Req to Mike.

- Address any corrections from QC.

8. Complete Government Walkthrough

Due: 21st

- PM and Superintendent review completed work with the Government.

- Confirm billing percentages.

9. Make Government-Requested Revisions

Due: 22nd

- PM makes any agreed-upon changes.

- Send revised Pen Req back to the Government if needed.

10. Obtain CO/COR Buy-In

Due: 24th

- Resolve any remaining billing questions.

- Obtain Government agreement on billing percentages.

11. Send Approved Pen Req to Cashmere/Sue

Due: 25th

- PM sends the approved Pen Req for final processing.

12. Notarization & Drew's Signature

Due: 26th

Cashmere/Sue coordinates:

- Notarization

- Drew's signature

- Return of AIA to PM

13. Send AIA for CO/COR Signature

Due: 27th

- PM sends the finalized AIA to the Government for signature.

- PM follows up until received.

14. Return Signed AIA to Cashmere

Due: 29th

- PM sends the CO/COR-signed AIA back to Cashmere.

15. Upload AIA to Tungsten

Due: Last Business Day of the Month

- Cashmere uploads the completed AIA to Tungsten.

- Submission confirmation is sent to the appropriate team.

16. Check Invoice Status

Due: Within 48 Hours of Upload

- Cashmere checks Tungsten to confirm the invoice is moving through approval.

- Follow up with the appropriate Government contact if it remains in Received status.

Monthly Deadlines to Remember

19th: PM + Superintendent billing review complete
20th: Sub invoices/CPRs due + Pen Req completed + sent to Mike
21st: Government walkthrough complete
22nd: Government revisions complete
24th: CO/COR buy-in complete
25th: Approved Pen Req to Cashmere/Sue
26th: Notarization + Drew's signature
27th: AIA sent for Government signature
29th: Signed AIA returned to Cashmere
Last Business Day: AIA uploaded to Tungsten
Within 48 Hours: Invoice status checked