AIA Monthly Billing Process-Superintendent

Step-by-Step Guide

Superintendent's Role

The Superintendent is responsible for verifying completed work in the field, scheduling and performing the COR buy-in, and communicating any changes back to the PM.

1. Track Completed Work

Due: Ongoing – 1st through 19th

- Keep Daily Logs current.

- Track subcontractor progress.

- Keep the Three-Week Lookahead current.

- Know what work is complete onsite.

2. Review Billing with PM

Due: 19th

- Review completed work with the PM.

- Confirm subcontractor progress.

- Make sure billing percentages match actual field conditions.

- Identify anything that is not complete.

3. Confirm Pen Req with PM

Due: 20th

- Review the Pen Req with the PM before it is sent to Mike Paquet for QC.

- Confirm percentages accurately reflect completed work.

- If work is not complete by the billing cutoff, it moves to the next invoice.

4. Wait for QC Approval

Due: 20th

- PM sends the Pen Req to Mike Paquet for QC.

- Do not schedule the final COR buy-in until the Pen Req has been approved by Mike.

5. Schedule COR Buy-In

Due: 21st

- Once Mike approves the Pen Req:

  - Contact the COR.

  - Schedule the billing walkthrough/buy-in.

  - Coordinate with the PM so they know when the walkthrough will occur.

6. Perform COR Buy-In

Due: No Later Than the 23rd

- Walk the project with the COR and review:

  - Completed work

  - Percent complete

  - Billing percentages

- Confirm whether the COR agrees with the percentages shown on the Pen Req.

7. Send COR Feedback to PM

Due: Same Day as Buy-In

- Immediately communicate the results to the PM.

- Tell the PM:

  - What the COR approved

  - What the COR questioned

  - Any percentage changes

- Any items that need to be removed or revised

8. PM Revises Pen Req, If Needed

Due: 24th

- PM makes any necessary revisions based on the COR buy-in.

- Superintendent provides clarification if needed.

9. Confirm Final Buy-In

Due: 24th

- Confirm all COR comments have been addressed.

- Make sure the PM has the information needed to finalize the Pen Req.

The Superintendent’s responsibility is complete once COR buy-in is confirmed and all feedback has been provided to the PM.

Superintendent Deadlines

19th — Review completed work with PM

20th — Confirm Pen Req before QC

21st — Schedule COR buy-in after Mike's approval

23rd — COR buy-in completed

Same Day — Send COR feedback to PM

24th — All COR comments resolved

Remember: Verify → Schedule → Walk → Communicate

Your responsibility is to make sure the percentage completed on the AIA reflects what is actually complete in the field and that the PM receives all information from the COR buy-in in time to finalize the billing.