- Fill out the template:

  - Select contract type:

PO: if under $10,000, material only, or work already complete

Bond : if over $250,000

  - Scope of Work

    - If summarizing the SOW instead of copying it fully, end with:

    - “SOW attached here too, incorporated herein by reference.”

  - Estimated Start Date

    - Use the day after buyout is signed and sent internally for QC.

    - If work already started, use actual start date.

  - Estimated Completion Date

    - Must NOT be the CCD.

    - Must allow buffer time before CCD.

- File in Dropbox in subcontractor folder in correct project and save as the following:

  - Unsigned Buyout → “Sub Name Buyout”

  - Signed Buyout (PM/CM signed) → “Sub Name Buyoutx”

  - Proposal → “Sub Name Proposal”

- Send the Buyout for Internal Review

  - Do not send the approval email until all documents are saved in Dropbox.

  - Send the buyout to Mike Paquet and Finance.

- . Explain Anything the Reviewers Need to Know

  - The email should identify anything that Finance and Operations need to know before approval.

  - Include special payment terms, unusual requirements, budget concerns, cost code issues, or anything that could delay processing.

  - If the buyout is over budget, explain why and identify where the funds should be pulled from.

  - If it is a Change Order, explain why the Change Order is being processed and provide the necessary supporting information.

- . Complete Internal Review

  - Mike reviews the buyout against the budget.

  - If revisions are required it is returned to the PM to revise and resubmit back to Mike.

  - Once approved, Mike forwards the approved buyout to Laurie/Finance and copies the appropriate project team.

- Finance Prepares the Contract

  - Laurie makes the necessary budget adjustments in Intacct and prepares the contract documents for the subcontractor.

  - The contract goes through the required internal signatures before being sent to the subcontractor.

- Subcontractor Receives the Contract

  - The contract is sent to the subcontractor through DocuSign.

  - The subcontractor has approximately one week to sign. BD follows up with the subcontractor while the contract is in DocuSign.

- Obtain Final Signature

  - After the subcontractor signs, the contract continues through the remaining DocuSign approvals.

- Drew's signature is the final signature.

  - The subcontract is not fully executed until all required signatures are complete.

- Confirm Fully Executed Contract

  - Confirm the contract has been fully executed and properly filed.